## Project Launch Plan
Task Name | Status | Health | Start Date | End Date | Duration
Planning Phase |  |  | 2019-09-26 | 2019-10-22 | 19d
Review Challenge Requirements and Create Project Schedule | Complete | Green | 2019-09-26 | 2019-10-03 | 6d
Brainstorm and Research Solutions | Complete | Green | 2019-09-26 | 2019-10-10 | 11d
Continue Research Solutions and Begin Proposal | Complete | Green | 2019-10-10 | 2019-10-17 | 6d
Write Proposal and receive necessary signatures from administration | In Progress | Yellow | 2019-10-17 | 2019-10-22 | 4d
Construct Suit |  |  | 2019-10-01 | 2020-02-21 | 104d
Set Up Raspberry Pi & Network | Complete | Green | 2019-10-01 | 2019-10-09 | 7d
Build Ultra Wide Band Radios | In Progress | Yellow | 2019-12-08 | 2019-12-20 | 11d
Add Camera to Network for SLAM | In Progress | Yellow | 2019-12-01 | 2020-02-21 | 61d
Construct LED Matrix for lighting | In Progress | Yellow | 2020-01-05 | 2020-01-08 | 4d
ROS Network | In Progress | Yellow | 2019-12-01 | 2019-12-13 | 11d
SLAM Algorithm | In Progress | Yellow | 2020-01-05 | 2020-01-31 | 21d
UWB Radio Software | In Progress | Yellow | 2020-01-05 | 2020-01-31 | 21d
LED Camera Vision Tracking | In Progress | Yellow | 2020-01-26 | 2020-02-07 | 11d
Web Interface for Task and Ground Control | In Progress | Yellow | 2020-02-02 | 2020-02-14 | 11d
HOLO Lens Interface | In Progress | Yellow | 2020-01-26 | 2020-02-21 | 21d
Suit Testing & Revisions |  |  | 2020-02-24 | 2020-03-25 | 23d
Major Test 1 | In Progress | Yellow | 2020-02-24 | 2020-02-28 | 5d
Major Adjustments 1 | In Progress | Yellow | 2020-03-01 | 2020-03-05 | 5d
Major Test 2 | In Progress | Yellow | 2020-03-05 | 2020-03-06 | 2d
Major Adjustments 2 | In Progress | Yellow | 2020-03-03 | 2020-03-06 | 4d
Final Major Test | In Progress | Yellow | 2020-03-12 | 2020-03-18 | 5d
Final Major Adjustments | In Progress | Yellow | 2020-03-19 | 2020-03-25 | 5d
Ensure Suit is Ready for Houston |  |  | 2020-03-25 | 2020-04-22 | 21d
Complete final tests for minor adjustments to be made | In Progress | Yellow | 2020-03-25 | 2020-03-25 | 1d
Complete final minor adjustments | In Progress | Yellow | 2020-03-30 | 2020-03-30 | 1d
Prepare equipment for travel | In Progress | Yellow | 2020-04-15 | 2020-04-15 | 1d
Attend NASA Suits Challenge 2020 | In Progress | Yellow | 2020-04-22 | 2020-04-22 | 1d
Complete Public Outreach |  |  | 2020-03-30 | 2020-05-15 | 35d
Attend Bayonne High School | In Progress | Yellow | 2020-05-01 | 2020-05-15 | 11d
Attend OTHER SCHOOL | In Progress | Yellow | 2020-03-30 | 2020-04-15 | 13d

## Comments
Row 4 | Business case examples Anyone have a business case format that has worked for you in the past? | Eric Browne | 06/02/09 6:15 PM
| The attached version worked well for me. | Burke Boyd | 06/02/09 8:07 PM
| I think we’ll need to hire an outside design firm for this project. | Eric Browne | 06/15/09 3:19 PM
| I agree. | Kelly Smart | 10/20/11 6:52 PM
Row 10 | Product Positioning I have created a product launch folder for us. Included is the social media plan for M2 Product Launch. Please share your feedback | Paul Finley | 04/12/16 10:52 AM
Row 18 | Social plan looks good | Michelle Kimihira | 08/30/16 11:01 AM
Row 18 | I have created a launch folder for us. Included is the social media plan for B2 Product Launch. Please share your feedback | Paul Finley | 08/30/16 10:49 AM